## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Collect ANPR & ATCC datasets from Kaggle; validate image/video quality | MUST HAVE | Kaggle Account | Kurugodu Sushma | completed
S1 | S1 | US-002 | Perform preprocessing: resizing, denoising, normalization for ANPR & ATCC | MUST HAVE | OpenCV | Kurugodu Sushma | Completed
S1 | S1 | US-003 | Conduct EDA on traffic patterns, plate styles, and vehicle classes | SHOULD HAVE | Python, Pandas | Kurugodu Sushma | Completed
S1 | S1 | US-004 | Set up YOLO + OCR environment; verify GPU support in Colab | VITAL | Kaggle GPU | Kurugodu Sushma | Completed
S2 | S2 | US-001 | Outlier removal & scaling for ANPR/ATCC numeric features | MUST HAVE | Pandas, NumPy | Kurugodu Sushma | Completed
S2 | S2 | US-002 | Encode labels + prepare plate metadata for ANPR training | MUST HAVE | Sklearn | Kurugodu Sushma | Completed
S2 | S2 | US-003 | Train YOLO models for ATCC + ANPR and evaluate performance | MUST HAVE | YOLOv8 | Kurugodu Sushma | Completed
S2 | S2 | US-004 | Select best model using metrics (mAP, F1); finalize ANPR model | MUST HAVE | YOLO Tools | Kurugodu Sushma | Completed
S2 | S2 | US-005 | Hyperparameter tuning + retrain for improved accuracy | MUST HAVE | YOLO Tuner | Kurugodu Sushma | Completed
S2 | S2 | US-006 | Export final models into onnx/pt format for deployment | MUST HAVE | YOLO Exporter | Kurugodu Sushma | Completed
S3 | S3 | US-001 | Create Streamlit ATCC UI to display detected vehicles & counts | MUST HAVE | Streamlit | Kurugodu Sushma | Completed
S3 | S3 | US-002 | Develop ANPR UI to upload images & show OCR output | MUST HAVE | Streamlit, OpenCV | Kurugodu Sushma | Completed
S3 | S3 | US-003 | Integrate OCR output with detected plate region (bounding box) | MUST HAVE | EasyOCR | Kurugodu Sushma | Completed
S3 | S3 | US-004 | Add analytics dashboard (bar, pie, line, scatter) for ATCC | SHOULD HAVE | Matplotlib / Pandas | Kurugodu Sushma | Completed
S3 | S3 | US-005 | Implement model logging (plate number, timestamp, frame ID) | COULD HAVE | CSV / JSON | Kurugodu Sushma | Completed
S3 | S3 | US-006 | Begin ANPR + ATCC module integration into single app | SHOULD HAVE | Streamlit | Kurugodu Sushma | Completed
S4 | S4 | US-001 | Full integration + testing of ANPR + ATCC Streamlit dashboard | MUST HAVE | Streamlit | Kurugodu Sushma | Completed
S4 | S4 | US-002 | Optimize inference time and improve UI responsiveness | MUST HAVE | Python, Streamlit | Kurugodu Sushma | Completed
S4 | S4 | US-003 | Create final PPT, documentation, video demo for submission | MUST HAVE | Docs / PPT | Kurugodu Sushma | Completed
S4 | S4 | US-004 | Prepare final project submission package by Dec 8 | MUST HAVE | Docs | Kurugodu Sushma | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 49 | 19 | 16 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TASK-001 | Setup project structure & GitHub repo | 2025-11-08 | 2025-11-08 | - | Setup | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Install YOLO, Streamlit, OCR dependencies | 2025-11-08 | 2025-11-09 | - | Environment Setup | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-003 | Upload ATCC dataset to Drive | 2025-11-09 | 2025-11-10 | - | Data Gathering | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-004 | Upload ANPR dataset to Drive | 2025-11-10 | 2025-11-11 | - | Data Gathering | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-005 | Perform EDA on ANPR & ATCC datasets | 2025-11-11 | 2025-11-14 | - | Data Analysis | Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-004 | TASK-006 | Extract frames from ATCC videos | 2025-11-15 | 2025-11-16 | - | Data Processing | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-007 | Train ATCC YOLO model (v8) | 2025-11-16 | 2025-11-18 | - | Model Training | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-008 | Train ANPR YOLO model | 2025-11-18 | 2025-11-20 | - | Model Training | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-009 | Test OCR results using EasyOCR | 2025-11-20 | 2025-11-21 | - | OCR Testing | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TASK-010 | Export YOLO results to CSV | 2025-11-21 | 2025-11-21 | - | Data Export | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-007 | TASK-011 | Build Streamlit ATCC UI | 2025-11-22 | 2025-11-24 | - | Frontend | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TASK-012 | Build Streamlit ANPR UI | 2025-11-24 | 2025-11-26 | - | Frontend | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-013 | Integrate YOLO models inside Streamlit | 2025-11-26 | 2025-11-28 | - | Integration | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-014 | Add charts (bar, pie, line, scatter) | 2025-11-28 | 2025-11-30 | - | Visualization | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TASK-015 | Setup SQLite DB for storing logs | 2025-11-30 | 2025-12-01 | - | Database | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-010 | TASK-016 | UI polishing for ATCC & ANPR dashboards | 2025-12-02 | 2025-12-04 | - | UI/UX | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TASK-017 | Full testing (ATCC + ANPR workflows) | 2025-12-04 | 2025-12-06 | - | Testing | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TASK-018 | Debug & fix performance issues | 2025-12-06 | 2025-12-08 | - | Debugging | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TASK-019 | Deploy final Streamlit app in VS Code | 2025-12-08 | 2025-12-09 | - | Deployment | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TASK-020 | Prepare documentation & demo | 2025-12-09 | 2025-12-11 | - | Documentation | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Large ATCC dataset | Used lower-resolution videos
S1 | Day 3 | YOLO installation errors | Reinstalled stable version
S1 | Day 5 | Uneven ANPR image sizes | Resized images
S2 | Day 2 | Poor night detection | Improved brightness
S2 | Day 4 | Plate not detected | Tuned confidence
S2 | Day 6 | Slow video processing | Added frame skipping
S3 | Day 1 | Video not loading in app | Fixed temp file handling
S3 | Day 3 | Graphs not centered | Updated layout
S3 | Day 5 | Noisy plate OCR | Applied filtering
S4 | Day 1 | UI misalignment | Adjusted layout width
S4 | Day 3 | App runtime errors | Reinstalled dependencies
S4 | Day 4 | Module integration issue | Refactored code

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-04 | 2025-11-17 | Kurugodu Sushma | Exploring YOLO models and dataset structure | Delaying dataset preprocessing | Regular data gathering and documentation | understanding datasets
2 | S2 | 2025-11-18 | 2025-11-25 | Kurugodu Sushma | Applying preprocessing techniques for ATCC & ANPR | Skipping model evaluation steps | Experimenting with training runs | preprocessing workflows
3 | S3 | 2025-11-26 | 2025-12-03 | Kurugodu Sushma | Integrating ANPR OCR and ATCC detection in Streamlit | Applying changes without version tracking | Maintaining project workflow and backups | Successful integration
4 | S4 | 2025-12-04 | 2025-12-08 | Kurugodu Sushma | Improving UI & analytics dashboard for ATCC | Unnecessary repeated testing without logs | Reading documentation & refining code | Gained better UI experience